AGENTIC EHR

Production Prototype Roadmap

From 9-Module Demo to FHIR-Compliant, AI-Native Clinical System

Dr. Michael Renner

ImpactMed Consulting, LLC

April 2, 2026

Repository: github.com/mjrgman/AI-EHR

Branch: main (f66be4a) | 19 commits | 9 clinical modules

# Executive Summary

This roadmap converts the Agentic EHR from a working 9-module clinical demo into a production-grade prototype capable of FHIR interoperability, HIPAA-compliant AI layering, and integration with existing health systems. The system is not starting from zero. It already has a multi-agent orchestrator, CDS engine with clinical thresholds, HIPAA middleware with AES-256-GCM encryption, billing/scheduling modules, and Docker deployment. Five gaps separate this from a production prototype.

## Current State Assessment

| Component | Current Stack | Status | Production Target |
| --- | --- | --- | --- |
| Backend | Express.js + SQLite3 | Built | Express + PostgreSQL + FHIR |
| Frontend | React 18 + Vite + Tailwind | Built | React + Medplum UI components |
| AI Engine | Claude API + pattern fallback | Built | Claude + LangChain RAG |
| Agent System | 9 modules + orchestrator | Built | 9 modules + MCP integration |
| CDS Engine | Rule-based + HEART score | Built | Rules + AI-augmented CDS |
| Security | AES-256, RBAC, audit logs | Built | BAA-ready, penetration tested |
| FHIR | Research docs only | Not Started | FHIR R4 facade + SMART-on-FHIR |
| Database | SQLite (single-user) | Partial | PostgreSQL + pgvector |
| RAG / Vector | None | Not Started | pgvector + LangChain.js |
| Voice Pipeline | Web Speech API (browser) | Partial | Deepgram/AssemblyAI streaming |
| Interop Platform | None | Research Only | Medplum FHIR server |

## Five Gaps to Production

Gap 1: FHIR R4 interoperability (no implementation, only research). Gap 2: Database migration from SQLite to PostgreSQL. Gap 3: RAG/vector search for agent memory and clinical knowledge retrieval. Gap 4: Production voice pipeline with speaker diarization. Gap 5: Medplum integration for managed FHIR compliance and SMART-on-FHIR launch support.

# Gap 1: FHIR R4 Interoperability

Priority: Critical. Without FHIR, the system cannot exchange data with Epic, Cerner, Athenahealth, or any ONC-certified EHR. This is the single largest barrier to pilot deployment.

### Current State

FHIR appears in VISION.md (Phase 6) and research/TOOLS-AND-REPOS.md (detailed notes on fhir-py, HAPI FHIR, SMART-on-FHIR, Google Cloud Healthcare API). Zero FHIR resources exist in code. The database uses custom SQLite tables (patients, problems, medications, encounters) with a proprietary schema. No SMART-on-FHIR, no HL7 v2 interfaces, no NCPDP SCRIPT.

### Architecture Decision

Approach: FHIR Translation Layer (Facade Pattern). Add FHIR R4 endpoints to the existing Express server without replacing the backend. Use @medplum/fhir-router as middleware mounted at /fhir/*. Custom adapters translate between internal SQLite/PostgreSQL schema and FHIR resources.

### FHIR Resource Mapping

| FHIR Resource | Internal Table(s) | Agent Owner | Priority |
| --- | --- | --- | --- |
| Patient | patients | Front Desk | Sprint 1 |
| Encounter | encounters | Scribe / Physician | Sprint 1 |
| Observation | vitals, lab_results | MA / CDS | Sprint 1 |
| Condition | problems | Physician / CDS | Sprint 1 |
| MedicationRequest | medications, prescriptions | Orders | Sprint 2 |
| AllergyIntolerance | allergies | CDS | Sprint 2 |
| DiagnosticReport | lab_results (grouped) | Orders | Sprint 2 |
| ServiceRequest | orders | Orders | Sprint 3 |
| DocumentReference | encounter_notes (SOAP) | Scribe | Sprint 3 |
| CarePlan | treatment_plans | Physician / Quality | Sprint 3 |

### Implementation Steps

Sprint 1 (Week 1-2): Install @medplum/fhir-router and @medplum/definitions. Create server/fhir/ directory with adapter modules. Implement Patient, Encounter, Observation, and Condition endpoints. Write integration tests against FHIR validator. Mount at /fhir/* alongside existing /api/* routes.

Sprint 2 (Week 3-4): Add MedicationRequest, AllergyIntolerance, DiagnosticReport. Implement FHIR search parameters (_id, patient, date, code). Add Bundle support for batch operations.

Sprint 3 (Week 5-6): ServiceRequest, DocumentReference, CarePlan. Implement $everything operation on Patient. Add FHIR capability statement (/fhir/metadata).

### SMART-on-FHIR Launch

SMART-on-FHIR enables the app to launch inside Epic, Cerner, or other EHRs. Requires OAuth2 Authorization Code flow with PKCE. Register as a ClientApplication with the target EHR. Implement launch context handling (patient ID passed via launch parameter). Scope negotiation (patient/*.read, patient/*.write). Token validation middleware on all /fhir/* endpoints. Target: Sprint 4-5.

# Gap 2: PostgreSQL Migration

Priority: High. SQLite cannot support concurrent users, multi-process access, or the pgvector extension needed for RAG. This migration unlocks Gaps 3 and 5.

### Migration Strategy

Use Prisma as the migration tool. It generates migration files from schema changes, supports both SQLite and PostgreSQL as targets, and provides type-safe queries. Migration is incremental: switch the datasource provider from sqlite to postgresql, run prisma migrate deploy, import data from SQLite dump.

### Schema Translation

| SQLite Pattern | PostgreSQL Equivalent | Notes |
| --- | --- | --- |
| INTEGER PRIMARY KEY AUTOINCREMENT | UUID DEFAULT gen_random_uuid() | Use UUIDs for FHIR compat |
| TEXT | VARCHAR or TEXT | Add CHECK constraints |
| DATETIME DEFAULT CURRENT_TIMESTAMP | TIMESTAMPTZ DEFAULT NOW() | Use timezone-aware |
| PRAGMA journal_mode = WAL | Built-in MVCC | No pragma needed |
| PRAGMA foreign_keys = ON | Default ON in PostgreSQL | Enforced by default |

### HIPAA Hardening for PostgreSQL

Encryption at rest: Use AWS RDS encryption or pgcrypto extension for field-level encryption of PHI columns. Encryption in transit: Enforce SSL/TLS on all connections (ssl: require in pg config). Row-level security: Enable RLS policies for multi-tenant isolation. Audit logging: Deploy pgaudit extension or continue using the existing audit-logger.js middleware. Backup encryption: All database backups encrypted with AES-256.

### Implementation Steps

Sprint 2 (parallel with FHIR Sprint 2): Install Prisma. Generate initial schema from existing SQLite tables. Switch datasource to PostgreSQL. Run migration against local PostgreSQL instance. Write data import script (SQLite dump to PostgreSQL). Verify all 24+ existing tables migrate cleanly. Update database.js to use Prisma client instead of raw sqlite3.

# Gap 3: RAG / Vector Search for Agent Memory

Priority: High. Transforms agents from stateless LLM calls into context-aware clinical assistants that retrieve relevant patient history, guidelines, and prior decisions.

### Architecture Decision

Approach: pgvector inside PostgreSQL. No separate vector database. pgvector adds vector similarity search as a PostgreSQL extension. This keeps all data in one encrypted, HIPAA-compliant database. Sufficient latency for clinical decision support (50-200ms). Cost: $0 additional.

### What Gets Embedded

| Content Type | Source | Agent Consumer | Update Frequency |
| --- | --- | --- | --- |
| Patient encounter notes | encounter_notes table | Physician, Scribe, CDS | Per encounter |
| Clinical guidelines | Loaded from USPSTF, AHA | CDS, Quality | Monthly |
| Provider preferences | provider_learning table | Physician, Scribe | Per session |
| Drug interactions | Loaded from FDA/NLM | CDS, Orders | Weekly |
| Prior authorization rules | Payer-specific docs | Orders, Coding | Quarterly |

### Tech Stack

Vector store: pgvector extension on PostgreSQL (vector(1536) columns for OpenAI ada-002 embeddings). Embedding model: text-embedding-3-small (OpenAI) or Anthropic embeddings when available. Orchestration: @langchain/core + @langchain/anthropic + @langchain/community/vectorstores/postgres. RAG chain: createRetrievalChain with top-5 similarity search, filtered by patient_id for access control.

### Implementation Steps

Sprint 3 (after PostgreSQL migration): Enable pgvector extension. Create clinical_documents table with vector(1536) column. Build embedding pipeline: encounter notes run through text splitter, embedded, stored. Update agent-memory.js to use vector retrieval instead of SQLite key-value lookups. Wire CDS agent to retrieve relevant guidelines via RAG before generating suggestions. Add de-identification step before embedding (strip names, MRNs, SSNs).

# Gap 4: Production Voice Pipeline

Priority: Medium-High. The ambient scribe module is the flagship feature. Web Speech API works for demos but lacks speaker diarization, medical vocabulary, and HIPAA compliance.

### Provider Comparison

| Provider | Real-Time | Diarization | BAA | Cost/min | Best For |
| --- | --- | --- | --- | --- | --- |
| Deepgram Nova-2 | Yes (WS) | Yes | Available | $0.0043 | Interactive agents |
| AssemblyAI | Yes (stream) | Yes (native) | Available | $0.0025 | Batch transcription |
| OpenAI Whisper | No (async) | No | No BAA | $0.02 | Offline only |

### Architecture Decision

Approach: Dual provider. Deepgram for real-time interactive transcription during encounters (low latency, 400ms first word). AssemblyAI for post-encounter batch processing and quality assurance (lower cost, native diarization). Both providers offer HIPAA BAAs.

### Implementation Steps

Sprint 4 (Week 7-8): Sign BAA with Deepgram. Replace Web Speech API in useSpeechRecognition.js with Deepgram WebSocket client. Add server-side proxy for API key security. Implement speaker diarization labels (provider vs. patient). Feed diarized transcripts to Scribe agent for SOAP section placement.

Sprint 5 (Week 9-10): Add AssemblyAI for post-encounter batch verification. Build audio recording pipeline (encrypted storage, 30-day retention). Implement medical vocabulary boosting. Integration test: full encounter flow from voice input through SOAP note generation to FHIR DocumentReference.

# Gap 5: Medplum Integration

Priority: Medium. Medplum provides a managed FHIR server, SMART-on-FHIR auth, React components, and MCP support for AI agents. It accelerates Gaps 1 and 3 but requires architectural alignment.

### Integration Strategy

Approach: Medplum as FHIR CDR alongside existing Express backend. Medplum handles FHIR resource storage, OAuth2/SMART-on-FHIR authentication, and subscription-based workflows. The existing Express server retains custom business logic (billing, agent orchestration, CDS rules). Communication via @medplum/core SDK.

### What Medplum Replaces vs. Keeps

| Component | Medplum Handles | You Keep |
| --- | --- | --- |
| FHIR Storage | Full CDR, all resources | Custom SQLite tables (legacy) |
| Authentication | OAuth2, SMART-on-FHIR | JWT auth (existing, phase out) |
| Audit Logging | FHIR AuditEvent | audit-logger.js (supplement) |
| Subscriptions | Resource-triggered webhooks | Agent message bus (internal) |
| AI Integration | MCP server, $ai operation | Agent orchestrator (custom) |
| React Components | @medplum/react library | Custom pages (extend/replace) |

### Deployment

Self-hosted via Docker Compose (PostgreSQL + Redis + Medplum Server + Medplum App). Local development: docker compose up -d with full-stack YAML from Medplum repo. Production: AWS CDK deployment or Medplum Cloud with BAA. Medplum server runs on port 8103; existing Express server on port 3000. Nginx reverse proxy routes /fhir/* to Medplum, /api/* to Express.

### Implementation Steps

Sprint 5-6 (Week 9-12): Deploy Medplum Docker stack locally. Configure ClientApplication for SMART-on-FHIR. Migrate FHIR facade endpoints to Medplum CDR (replace custom adapters with Medplum storage). Create Medplum Bots for agent triggers (e.g., new Encounter triggers Scribe agent). Wire @medplum/react components into existing React frontend. Test SMART-on-FHIR launch flow with Medplum sandbox.

# Master Implementation Timeline

| Sprint | Dates | Deliverables | Dependencies |
| --- | --- | --- | --- |
| 1 | Apr 7-18 | FHIR facade: Patient, Encounter, Observation, Condition endpoints | None |
| 2 | Apr 21 - May 2 | FHIR: MedicationRequest, AllergyIntolerance, DiagnosticReport. PostgreSQL migration with Prisma. | Sprint 1 |
| 3 | May 5-16 | FHIR: ServiceRequest, DocumentReference, CarePlan. pgvector + RAG pipeline. Agent memory upgrade. | Sprint 2 (PostgreSQL) |
| 4 | May 19-30 | Deepgram voice pipeline. Speaker diarization. Scribe agent integration. | Sprint 1 (FHIR) |
| 5 | Jun 1-12 | AssemblyAI batch pipeline. Medplum Docker deployment. SMART-on-FHIR auth flow. | Sprint 2-3 |
| 6 | Jun 15-26 | Medplum CDR migration. Bot-based agent triggers. React component integration. End-to-end integration test. | Sprint 5 |
| 7 | Jun 29 - Jul 10 | FHIR capability statement. Penetration testing. BAA documentation. Synthea test patient loading. | All sprints |

## Risk Register

| Risk | Severity | Mitigation | Owner |
| --- | --- | --- | --- |
| Medplum MCP is experimental (no PHI BAA from Claude) | High | Use $ai operation (OpenAI) for production PHI; Claude for synthetic data only | Architecture |
| FHIR facade diverges from Medplum CDR | Medium | Build facade as throw-away; migrate to Medplum storage in Sprint 6 | Engineering |
| pgvector performance on large datasets | Low | IVFFlat indexing; partition by patient_id; benchmark at 10K records | Database |
| Voice pipeline latency exceeds clinical threshold | Medium | Dual provider strategy; Deepgram for real-time, AssemblyAI for batch | Integration |
| SQLite to PostgreSQL data loss during migration | Medium | Row count verification script; parallel run period; rollback script | Database |

# Production Tech Stack Summary

| Layer | Technology | Version | Role |
| --- | --- | --- | --- |
| Frontend | React 18 + Vite + Tailwind + @medplum/react | 18.3 / 5.4 / 3.4 / 5.1 | Provider UI |
| Backend | Express.js + @medplum/fhir-router | 4.18 / 5.1 | REST API + FHIR facade |
| FHIR Server | Medplum Server (self-hosted Docker) | 5.1.6 | FHIR CDR + OAuth2 |
| Database | PostgreSQL 15+ with pgvector | 15.x / 0.7 | Clinical data + vectors |
| ORM | Prisma | 7.6 | Schema migrations + type-safe queries |
| AI Engine | Claude API (@anthropic-ai/sdk) | 0.39+ | Clinical reasoning |
| RAG | @langchain/core + @langchain/anthropic | 1.4 / 1.3 | Vector retrieval pipeline |
| Embeddings | OpenAI text-embedding-3-small | Latest | Document embeddings |
| Voice (Real-time) | Deepgram Nova-2 (WebSocket) | 5.0 | Live transcription |
| Voice (Batch) | AssemblyAI (streaming) | 4.29 | Post-encounter QA |
| Auth | OAuth2 + SMART-on-FHIR via Medplum | 5.1.6 | EHR launch + token mgmt |
| Deployment | Docker Compose + nginx | Latest | Multi-container orchestration |
| Testing | Synthea (synthetic patients) + FHIR validator | Latest | Clinical test data |

## Next Action

Sprint 1 begins April 7, 2026. First deliverable: FHIR R4 endpoints for Patient, Encounter, Observation, and Condition resources, mounted at /fhir/* alongside the existing /api/* Express routes. All code committed to mjrgman/AI-EHR on main branch.

Prepared by Dr. Michael Renner  |  ImpactMed Consulting, LLC  |  April 2, 2026